## Sheet1
S.No | Bug ID | Module | Bug Name | Bug Description | Expected Result | Actual Result | Type | Priority | Severity | Status | Action | Assigned To | Reported Date | MK Code Name | Code / Files Changed | Fix Description | Fixed By | Fix Date | QA Status | Deployment Version | Remarks
1 | BUG-001 | Profile / Location | Unknown Street Displayed for Current Location | Selecting Use Current Location generated the street address as "Unknown Street". | Actual street address should be displayed based on GPS/geocoding. | "Unknown Street" was displayed instead of the correct address. | Bug | Medium | High | Fixed | Resolved | Sai | 2026-01-07 | MY PROFILE |  | Updated the reverse geocoding logic to fetch and display the correct street address instead of the default "Unknown Street" value. Added proper fallback handling when address components are unavailable. | Sai | 2026-07-01 | Passed | v1.5.0 (or your version) | Ready for Deployment
2 | BUG-003 | Footer | Incorrect YouTube Link in Footer | The Follow Us → YouTube link redirected to an incorrect YouTube page instead of the official channel. | Footer YouTube link should open the official ManaKirana YouTube channel. | Incorrect YouTube page opened. | Bug | Low | Medium | Fixed | Resolved | Sai | 2026-01-07 | Footer |  | Updated the YouTube URL in the footer to point to the official ManaKirana YouTube channel and verified that the link redirects correctly. | Sai | 2026-07-01 | Passed | v1.5.0 (or your deployment version) | Ready for Deployment
3 | BUG-011 | Website Footer | Footer Quick Links Not Working | Home and Products links in the footer did not work initially. They started working only after clicking the Cart link. | Home, Products, and Cart links should navigate correctly whenever clicked. | Home and Products links were not clickable until the Cart link was clicked. | Bug | High | High | Fixed | Resolved | Sai | 2026-01-07 | Footer Navigation |  | Fixed the footer navigation logic to ensure all quick links (Home, Products, and Cart) navigate correctly on the first click without requiring any prior navigation. | Sai | 2026-07-03 | Passed | v1.5.0 (replace with your deployment version) | Ready for Deployment
4 | TC-HOME-001 | Home Page – Top Picks | Product Card Navigation from Top Picks Carousel | Clicking a product card in the Top Picks carousel did not consistently navigate to the Product Details page. | Clicking a product card should always navigate to the correct Product Details page. | Product card now opens the correct Product Details page without affecting carousel functionality. | Bug Fix | Medium | Medium | Fixed | Resolved | Sai | 2026-03-07 | Top Picks |  | Updated the product card click event to ensure reliable navigation to the Product Details page while maintaining normal carousel scrolling behavior. | Sai | 2026-07-03 | Passed | v1.5.0 | Ready for Deployment
5 | BUG-008 | Categories | Eggs & Dairy Category Not Opening | Opening the Eggs & Dairy category resulted in a 404 backend error. | The Eggs & Dairy category page should open successfully and display the products. | The category page now opens successfully without any 404 error. | Bug | High | High | Fixed | Resolved | Sai | 2026-01-07 | Category Navigation |  | Fixed the category routing/API mapping to ensure the Eggs & Dairy category loads successfully without returning a 404 error. | Sai | 2026-07-03 | Passed | v1.5.0 | Ready for Deployment